## Ark1
Gantt chart		november					december					december
Semester Exam		2	3	4	5	6	9	10	11	12	13	16	17	18	19	20	23	24	25	26	27	30	1	2	3	4	5	6
		Week 45					Week 46					Week 47					Week 48					Week 49
	Est. hours	M	Tu	W	Th	F	M	Tu	W	Th	F	M	Tu	W	Th	F	M	Tu	W	Th	F	M	Tu	W	Th	F	Sa	Su
Plan	6
Writing functional spec	3
Creating Gantt chart	3

Research	22
Target audience	3
Personae	6
Find relevant API	2
Colour and font profile	4
Look at similar websites	4
Plan what pages to include	3

Design	32
Paper sketches	8
Illustrations and prototype	24

Code	118
Code HTML mobile first	13
Code CSS basics/mobile	26
Code Javascript	65
Code CSS media queries	14

Test	10
Check for responsiveness	4
Check for errors in code	4
Check for WCAG	2

Report	22
Make notes during work	4
Put notes together and write report	16
Proofreading/adding images	2

Delivery

Total hours	210
Average hours per week	42